## Readme
Lecture 15 · Robot cell (cobot + CV/AI, on-prem, Jetson, ROS 2) · estimate model
Embedded Software Engineering, KPI · prepared 03.11.2026 · all rates, prices and durations are illustrative teaching values, not market rates.
How to use
Blue cells are inputs: O / M / P durations (working days), FTE allocations, rates, risks, materials, start date. Black cells are formulas; green cells link to another sheet.
WBS: PERT expected duration E = (O + 4M + P) / 6 and sigma = (P − O) / 6; ES/EF forward pass, LS/LF backward pass, float and the critical path recalculate when you change inputs.
Gantt: the week grid is drawn by conditional formatting from ES/EF; the critical path is shown in bold.
Team: person-days by role = Σ (E × FTE) + PM level of effort over the project length; cost and sell = person-days × rate.
Risks: expected value (EMV) = probability × impact. Summary: P50/P80 are pasted from the Monte Carlo script (20 000 runs) and are NOT live — rerun model.py after changing inputs.
Example row format (WBS): 2.4 ¦ 2 ¦ WP ¦ Tool PCB: schematic, PCB, BoM ¦ work ¦ 10 ¦ 15 ¦ 22 ¦ deps 2.2 ¦ HW 1.0
Units: durations in working days (5 per week), money in EUR.

## Summary
Full estimate and full timing
Schedule | Working days | Weeks | Date
Most-likely plan (CPM on M) | 186 | 37.2 | 2027-09-28
PERT plan (live, CPM on E) | 195.6667 | 39.1333 | 2027-10-12
Monte Carlo P50 | 220.4 | 44.08 | 2027-11-15
Monte Carlo P80 = commitment | 235.3 | 47.06 | 2027-12-06
Monte Carlo P90 | 243 | 48.6 | 2027-12-16
Blue values come from model.py (Monte Carlo, 20 000 runs) and are not live.
Price by phase | Model | Labour sell P50, € | Labour sell P80, € | Estimate / price, € | Upper bound, € | Rule
R&D | FP | 46500 | 51200 | 56300 | 56300 | FP = P80 × (1 + premium)
PoC | FP | 35000 | 39400 | 43300 | 43300 | FP = P80 × (1 + premium)
MVP | T&M^ | 28900 | 33300 | 28900 | 33300 | estimate = P50, cap = P80
Working packages (engineering) | T&M^ | 267500 | 286800 | 267500 | 286800 | estimate = P50, cap = P80
Finalisation | FP | 6400 | 7400 | 8100 | 8100 | FP = P80 × (1 + premium)
PoC kit (materials, pass-through) | T&M |  |  | 5000 | 5000 | cost × (1 + fee)
Materials and vendors for working packages | T&M |  |  | 79500 | 79500 | cost × (1 + fee)
Total |  |  |  | 488600 | 512300
Internal check: labour cost P50 / P80, € (model.py) |  | 213500 | 228000
Internal check: deterministic labour cost / sell (live) |  | 192974.3333 | 347448.8333
All values are illustrative teaching numbers for lecture 15; they are not a quotation.
Formulas:
Date = WORKDAY(Rates!$C18,ROUND([Working days],0))

## Rates
Role | Name | Cost per day, € | Sell (T&M) per day, € | Sell / cost
PM | Delivery / engineering manager | 300 | 540 | 1.8
SA | System architect | 340 | 610 | 1.7941
ROS | Robotics engineer (ROS 2, MoveIt 2) | 300 | 540 | 1.8
CV | CV/ML engineer | 320 | 580 | 1.8125
SW | Software engineer (HMI, on-prem, MLOps) | 260 | 470 | 1.8077
FW | Firmware engineer | 280 | 500 | 1.7857
HW | Hardware engineer | 280 | 500 | 1.7857
ME | Mechanical engineer | 250 | 450 | 1.8
SAF | Safety engineer (part-time) | 360 | 650 | 1.8056
QA | V&V / test engineer | 220 | 400 | 1.8182
TECH | Technician (assembly, harness) | 140 | 250 | 1.7857
PROC | Procurement manager | 180 | 320 | 1.7778
| PM level of effort (FTE over whole project) | 0.5
| Procurement handling fee on pass-through | 8%
| FP premium for penalty exposure | 10%
| Project start date (Monday) | 2027-01-11
Rates are illustrative course values (cf. lecture 12: 400 USD/day example), not market data.

## WBS
WBS, PERT and critical path (durations in working days) | [17 empty] | sell rate → |  |  | 540 | 610 | 540 | 580 | 470 | 500 | 500 | 450 | 650 | 400 | 250 | 320
[18 empty] | cost rate → |  |  | 300 | 340 | 300 | 320 | 260 | 280 | 280 | 250 | 360 | 220 | 140 | 180
ID | Epic | Phase | Task | Kind | Depends on | Gate | O | M | P | E (PERT) | σ | ES | EF | LS | LF | Float | Critical | Effort, pd | Cost, € | Sell, € | PM | SA | ROS | CV | SW | FW | HW | ME | SAF | QA | TECH | PROC
1.1 | 1 | R&D | Discovery: site, parts, IT policy | work |  | G1 | 5 | 8 | 15 | 8.6667 | 1.6667 | 0 | 8.6667 | 0 | 8.6667 | 0 | yes | 21.6667 | 6933.3333 | 12480 | 0.5 | 1 | 0.5 | 0.5
1.2 | 1 | R&D | System requirements + acceptance | work | 1.1 | G2 | 5 | 8 | 12 | 8.1667 | 1.1667 | 8.6667 | 16.8333 | 8.6667 | 16.8333 | 0 | yes | 15.5167 | 4932.6667 | 8877.1667 | 0.3 | 1 | [6 empty] | 0.3 | 0.3
1.3 | 1 | R&D | Architecture (ROS graph, compute) | work | 1.2 |  | 5 | 8 | 12 | 8.1667 | 1.1667 | 16.8333 | 25 | 16.8333 | 25 | 0 | yes | 19.6 | 6108.6667 | 10984.1667 |  | 1 | 0.5 | 0.3 | 0.3 |  | 0.3
1.4 | 1 | R&D | HARA + project risk register | work | 1.3 |  | 2 | 3 | 5 | 3.1667 | 0.5 | 25 | 28.1667 | 25 | 28.1667 | 0 | yes | 8.55 | 2751.8333 | 4952.6667 | 0.3 | 0.5 | 0.3 |  |  |  | 0.3 | 0.3 | 1
1.5 | 1 | PoC | PoC kit: Jetson, cameras, parts | wait | 1.1 |  | 5 | 10 | 20 | 10.8333 | 2.5 | 8.6667 | 19.5 | 17.3333 | 28.1667 | 8.6667 |  | 2.1667 | 390 | 693.3333 | [11 empty] | 0.2
1.6 | 1 | PoC | PoC-A: inference on Jetson | work | 1.4, 1.5 |  | 10 | 15 | 25 | 15.8333 | 2.5 | 28.1667 | 44 | 28.1667 | 44 | 0 | yes | 20.5833 | 6301.6667 | 11415.8333 |  |  |  | 1 | 0.3
1.7 | 1 | PoC | PoC-B: grasp with ROS 2 + MoveIt 2 | work | 1.4, 1.5 |  | 8 | 12 | 20 | 12.6667 | 2 | 28.1667 | 40.8333 | 31.3333 | 44 | 3.1667 |  | 16.4667 | 4750 | 8550 |  |  | 1 |  |  |  |  | 0.3
1.8 | 1 | PoC | PoC review | work | 1.6, 1.7 | G3 | 1 | 2 | 3 | 2 | 0.33333 | 44 | 46 | 44 | 46 | 0 | yes | 4 | 1260 | 2270 | 0.5 | 0.5 | 0.5 | 0.5
1.9 | 1 | MVP | MVP: one part type, bench + sim | work | 1.8 |  | 10 | 15 | 22 | 15.3333 | 2 | 46 | 61.3333 | 84.1667 | 99.5 | 38.1667 |  | 46 | 13186.6667 | 23843.3333 |  |  | 1 | 1 | 0.5 |  |  |  |  | 0.5
2.1 | 2 | WP | Detailed SW/HW/Mech requirements | work | 1.8 |  | 4 | 6 | 10 | 6.3333 | 1 | 46 | 52.3333 | 46 | 52.3333 | 0 | yes | 16.4667 | 4933.6667 | 8847.6667 |  | 1 | 0.3 |  |  | 0.3 | 0.5 | 0.5
2.2 | 2 | WP | HW load + component search | work | 2.1 | G4 | 3 | 5 | 10 | 5.5 | 1.1667 | 52.3333 | 57.8333 | 52.3333 | 57.8333 | 0 | yes | 9.9 | 2596 | 4636.5 |  | 0.3 |  |  |  |  | 1 |  |  |  |  | 0.5
2.3 | 2 | WP | Long-lead: cobot, Jetson, scanner | wait | 2.2 |  | 20 | 30 | 50 | 31.6667 | 5 | 57.8333 | 89.5 | 98.6667 | 130.3333 | 40.8333 |  | 6.3333 | 1140 | 2026.6667 | [11 empty] | 0.2
2.4 | 2 | WP | Tool PCB: schematic, PCB, BoM | work | 2.2 |  | 10 | 15 | 22 | 15.3333 | 2 | 57.8333 | 73.1667 | 57.8333 | 73.1667 | 0 | yes | 15.3333 | 4293.3333 | 7666.6667 | [6 empty] | 1
2.5 | 2 | WP | HW review (peer + FW) | work | 2.4 |  | 2 | 3 | 5 | 3.1667 | 0.5 | 73.1667 | 76.3333 | 85.8333 | 89 | 12.6667 |  | 3.1667 | 886.6667 | 1583.3333 | [5 empty] | 0.5 | 0.5
2.6 | 2 | WP | Mech design: tool, frame, guarding | work | 2.4 |  | 10 | 15 | 25 | 15.8333 | 2.5 | 73.1667 | 89 | 73.1667 | 89 | 0 | yes | 19 | 4845 | 8708.3333 | [6 empty] | 0.2 | 1
2.7 | 2 | WP | Mech review + rework + all hands | work | 2.5, 2.6 |  | 3 | 5 | 10 | 5.5 | 1.1667 | 89 | 94.5 | 89 | 94.5 | 0 | yes | 6.6 | 1831.5 | 3283.5 |  | 0.2 |  |  |  |  | 0.5 | 0.5
2.8 | 2 | WP | PCB manufacturing (vendor) | wait | 2.7 |  | 15 | 20 | 30 | 20.8333 | 2.5 | 94.5 | 115.3333 | 94.5 | 115.3333 | 0 | yes | 4.1667 | 1166.6667 | 2083.3333 | [6 empty] | 0.2
2.9 | 2 | WP | Mech manufacturing (vendor) | wait | 2.7 |  | 10 | 18 | 30 | 18.6667 | 3.3333 | 94.5 | 113.1667 | 96.6667 | 115.3333 | 2.1667 |  | 3.7333 | 933.3333 | 1680 | [7 empty] | 0.2
2.10 | 2 | WP | Standard parts + harness materials | wait | 2.7 |  | 10 | 15 | 25 | 15.8333 | 2.5 | 94.5 | 110.3333 | 99.5 | 115.3333 | 5 |  | 7.9167 | 1425 | 2533.3333 | [11 empty] | 0.5
2.11 | 2 | WP | Tool FW on dev board | work | 2.5 |  | 10 | 15 | 25 | 15.8333 | 2.5 | 76.3333 | 92.1667 | 108.1667 | 124 | 31.8333 |  | 15.8333 | 4433.3333 | 7916.6667 | [5 empty] | 1
2.12 | 2 | WP | Cabinet + harness build | work | 2.10 |  | 8 | 12 | 20 | 12.6667 | 2 | 110.3333 | 123 | 117.6667 | 130.3333 | 7.3333 |  | 19 | 3546.6667 | 6333.3333 | [6 empty] | 0.5 |  |  |  | 1
2.13 | 2 | WP | Assembly + review + rework | work | 2.8, 2.9, 2.10 |  | 5 | 8 | 15 | 8.6667 | 1.6667 | 115.3333 | 124 | 115.3333 | 124 | 0 | yes | 13.8667 | 2591.3333 | 4636.6667 | [6 empty] | 0.3 | 0.3 |  |  | 1
2.14 | 2 | WP | FW on real HW + bench test | work | 2.11, 2.13 |  | 4 | 6 | 10 | 6.3333 | 1 | 124 | 130.3333 | 124 | 130.3333 | 0 | yes | 9.5 | 2470 | 4433.3333 | [5 empty] | 1 |  |  |  | 0.5
2.15 | 2 | WP | Cell SW: orchestration, HMI, logs | work | 1.9 |  | 20 | 30 | 45 | 30.8333 | 4.1667 | 61.3333 | 92.1667 | 99.5 | 130.3333 | 38.1667 |  | 61.6667 | 17266.6667 | 31141.6667 |  |  | 1 |  | 1
2.16 | 2 | WP | Dataset v1 + 3 training iterations | work | 1.9 |  | 20 | 30 | 45 | 30.8333 | 4.1667 | 61.3333 | 92.1667 | 115.3333 | 146.1667 | 54 |  | 46.25 | 13135 | 23772.5 |  |  |  | 1 | 0.3 | [5 empty] | 0.2
2.17 | 2 | WP | On-prem GPU server, registry, OTA | work | 2.1 |  | 8 | 12 | 20 | 12.6667 | 2 | 52.3333 | 65 | 117.6667 | 130.3333 | 65.3333 |  | 8.8667 | 2508 | 4522 |  | 0.2 |  |  | 0.5
3.1 | 3 | WP | Cell integration at our site | work | 2.3, 2.12, 2.14, 2.15, 2.17 |  | 10 | 15 | 25 | 15.8333 | 2.5 | 130.3333 | 146.1667 | 130.3333 | 146.1667 | 0 | yes | 55.4167 | 14883.3333 | 26758.3333 |  |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 0.5
3.2 | 3 | WP | Safety validation | work | 3.1 |  | 5 | 8 | 15 | 8.6667 | 1.6667 | 146.1667 | 154.8333 | 150.1667 | 158.8333 | 4 |  | 17.3333 | 5373.3333 | 9706.6667 |  |  | 0.5 | [5 empty] | 1 | 0.5
3.3 | 3 | WP | Tuning: cycle time, accuracy | work | 3.1, 2.16 |  | 8 | 12 | 20 | 12.6667 | 2 | 146.1667 | 158.8333 | 146.1667 | 158.8333 | 0 | yes | 31.6667 | 9246.6667 | 16720 |  |  | 1 | 1 | [5 empty] | 0.5
3.4 | 3 | WP | FAT with customer | work | 3.2, 3.3 | FAT | 3 | 4 | 6 | 4.1667 | 0.5 | 158.8333 | 163 | 158.8333 | 163 | 0 | yes | 12.5 | 3541.6667 | 6395.8333 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 1
3.5 | 3 | WP | Shipping + customs | wait | 3.4 |  | 5 | 8 | 15 | 8.6667 | 1.6667 | 163 | 171.6667 | 163 | 171.6667 | 0 | yes | 1.7333 | 312 | 554.6667 | [11 empty] | 0.2
3.6 | 3 | WP | Installation + commissioning | work | 3.5 |  | 5 | 8 | 12 | 8.1667 | 1.1667 | 171.6667 | 179.8333 | 171.6667 | 179.8333 | 0 | yes | 22.8667 | 5586 | 10045 |  |  | 1 | 0.5 |  |  | 0.3 |  |  |  | 1
3.7 | 3 | WP | SAT + 2-week pilot run | work | 3.6 | SAT | 8 | 10 | 15 | 10.5 | 1.1667 | 179.8333 | 190.3333 | 179.8333 | 190.3333 | 0 | yes | 18.9 | 5355 | 9681 | 0.3 |  | 0.5 | 0.5 | [5 empty] | 0.5
3.8 | 3 | Final | Docs, training, handover | work | 3.7 |  | 4 | 5 | 8 | 5.3333 | 0.66667 | 190.3333 | 195.6667 | 190.3333 | 195.6667 | 0 | yes | 9.6 | 2709.3333 | 4885.3333 | 0.5 | 0.5 |  |  | 0.3 |  |  |  |  | 0.5
|  |  | Project finish (working days) | [9 empty] | 195.6667 |  |  |  |  | 592.1667 | 163624.3333 | 294618.8333

## Gantt
Gantt (weeks). Bars from WBS ES/EF via conditional formatting; bold = critical path.
ID | Task | ES | EF | Crit. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
1.1 | Discovery: site, parts, IT policy | 0 | 8.6667 | yes | [50 empty] | 1
1.2 | System requirements + acceptance | 8.6667 | 16.8333 | yes | [50 empty] | 1
1.3 | Architecture (ROS graph, compute) | 16.8333 | 25 | yes | [50 empty] | 1
1.4 | HARA + project risk register | 25 | 28.1667 | yes | [50 empty] | 1
1.5 | PoC kit: Jetson, cameras, parts | 8.6667 | 19.5 | [51 empty] | 1
1.6 | PoC-A: inference on Jetson | 28.1667 | 44 | yes | [50 empty] | 1
1.7 | PoC-B: grasp with ROS 2 + MoveIt 2 | 28.1667 | 40.8333 | [51 empty] | 1
1.8 | PoC review | 44 | 46 | yes | [50 empty] | 1
1.9 | MVP: one part type, bench + sim | 46 | 61.3333 | [51 empty] | 1
2.1 | Detailed SW/HW/Mech requirements | 46 | 52.3333 | yes | [50 empty] | 2
2.2 | HW load + component search | 52.3333 | 57.8333 | yes | [50 empty] | 2
2.3 | Long-lead: cobot, Jetson, scanner | 57.8333 | 89.5 | [51 empty] | 2
2.4 | Tool PCB: schematic, PCB, BoM | 57.8333 | 73.1667 | yes | [50 empty] | 2
2.5 | HW review (peer + FW) | 73.1667 | 76.3333 | [51 empty] | 2
2.6 | Mech design: tool, frame, guarding | 73.1667 | 89 | yes | [50 empty] | 2
2.7 | Mech review + rework + all hands | 89 | 94.5 | yes | [50 empty] | 2
2.8 | PCB manufacturing (vendor) | 94.5 | 115.3333 | yes | [50 empty] | 2
2.9 | Mech manufacturing (vendor) | 94.5 | 113.1667 | [51 empty] | 2
2.10 | Standard parts + harness materials | 94.5 | 110.3333 | [51 empty] | 2
2.11 | Tool FW on dev board | 76.3333 | 92.1667 | [51 empty] | 2
2.12 | Cabinet + harness build | 110.3333 | 123 | [51 empty] | 2
2.13 | Assembly + review + rework | 115.3333 | 124 | yes | [50 empty] | 2
2.14 | FW on real HW + bench test | 124 | 130.3333 | yes | [50 empty] | 2
2.15 | Cell SW: orchestration, HMI, logs | 61.3333 | 92.1667 | [51 empty] | 2
2.16 | Dataset v1 + 3 training iterations | 61.3333 | 92.1667 | [51 empty] | 2
2.17 | On-prem GPU server, registry, OTA | 52.3333 | 65 | [51 empty] | 2
3.1 | Cell integration at our site | 130.3333 | 146.1667 | yes | [50 empty] | 3
3.2 | Safety validation | 146.1667 | 154.8333 | [51 empty] | 3
3.3 | Tuning: cycle time, accuracy | 146.1667 | 158.8333 | yes | [50 empty] | 3
3.4 | FAT with customer | 158.8333 | 163 | yes | [50 empty] | 3
3.5 | Shipping + customs | 163 | 171.6667 | yes | [50 empty] | 3
3.6 | Installation + commissioning | 171.6667 | 179.8333 | yes | [50 empty] | 3
3.7 | SAT + 2-week pilot run | 179.8333 | 190.3333 | yes | [50 empty] | 3
3.8 | Docs, training, handover | 190.3333 | 195.6667 | yes | [50 empty] | 3

## Team
Role | Name | Person-days | Cost rate | Sell rate | Cost, € | Sell, € | Peak FTE (model.py) | Weeks active (model.py)
PM | Delivery / engineering manager | 114.4667 | 300 | 540 | 34340 | 61812 | 1 | 1–40
SA | System architect | 43.95 | 340 | 610 | 14943 | 26809.5 | 1 | 1–40
ROS | Robotics engineer (ROS 2, MoveIt 2) | 119.4333 | 300 | 540 | 35830 | 64494 | 1.48 | 1–39
CV | CV/ML engineer | 101.7833 | 320 | 580 | 32570.6667 | 59034.3333 | 1 | 1–39
SW | Software engineer (HMI, on-prem, MLOps) | 70.8 | 260 | 470 | 18408 | 33276 | 1.59 | 4–40
FW | Firmware engineer | 33.5667 | 280 | 500 | 9398.6667 | 16783.3333 | 1 | 10–30
HW | Hardware engineer | 58.3667 | 280 | 500 | 16342.6667 | 29183.3333 | 1 | 4–36
ME | Mechanical engineer | 32.8333 | 250 | 450 | 8208.3333 | 14775 | 1 | 6–25
SAF | Safety engineer (part-time) | 14.2833 | 360 | 650 | 5142 | 9284.1667 | 0.97 | 2–31
QA | V&V / test engineer | 36.0333 | 220 | 400 | 7927.3333 | 14413.3333 | 0.98 | 2–40
TECH | Technician (assembly, harness) | 43.5833 | 140 | 250 | 6101.6667 | 10895.8333 | 1.93 | 13–36
PROC | Procurement manager | 20.9 | 180 | 320 | 3762 | 6688 | 0.5 | 2–35
| Total | 690 |  |  | 192974.3333 | 347448.8333
| Average sell / cost |  |  |  |  | 1.8005
Peak FTE and weeks come from the weekly loading in model.py (static).

## Risks
ID | Risk | Task hit | Probability | Impact, days | Direct cost, € | EMV, days | EMV, € | Task float, days | On critical path?
R1 | Long-lead slip: Jetson production module / cobot | 2.3 | 30% | 20 | 0 | 6 | 0 | 40.8333 | absorbed
R2 | Accuracy below target on reflective parts: extra training iteration | 3.3 | 40% | 10 | 0 | 4 | 0 | 0 | yes
R3 | Second PCB spin | 2.8 | 30% | 15 | 1500 | 4.5 | 450 | 0 | yes
R4 | Customer IT security approval for on-prem server | 2.17 | 40% | 10 | 0 | 4 | 0 | 65.3333 | absorbed
R5 | ROS 2 driver for the chosen cobot immature | 1.7 | 25% | 8 | 0 | 2 | 0 | 3.1667 | yes
R6 | Risk assessment demands extra safety device | 3.2 | 25% | 10 | 3000 | 2.5 | 750 | 4 | yes
R7 | Key CV engineer leaves | 2.16 | 10% | 15 | 0 | 1.5 | 0 | 54 | absorbed
R8 | Shipping / customs delay | 3.5 | 40% | 7 | 500 | 2.8 | 200 | 0 | yes
| Sum of EMV (naive contingency) |  |  |  |  | 27.3 | 1400
| Monte Carlo: risks add to the finish (days), P50 / P80 |  |  |  |  | 12.5 | 16.1
A risk hitting a task with enough float does not move the finish: that is why the simulated impact is smaller than the naive sum.

## Materials
Item | Group | Phase | Amount, € | With handling fee, €
PoC kit: Jetson dev kit, 2 cameras, lighting, sample parts | Materials | PoC | 4600 | 4968
Collaborative 6-DoF robot (pilot cell) | Materials | WP | 30000 | 32400
Jetson production module + carrier + enclosure | Materials | WP | 2500 | 2700
Safety laser scanner + safety relay | Materials | WP | 4500 | 4860
Production cameras + lighting | Materials | WP | 2800 | 3024
On-prem GPU training server | Materials | WP | 12000 | 12960
Electrical cabinet components | Materials | WP | 3000 | 3240
End-effector BoM: vacuum, gripper actuators | Materials | WP | 2500 | 2700
PCB fabrication + assembly, 2 runs | Vendors | WP | 3000 | 3240
Mechanical fabrication: tool, frame, guarding | Vendors | WP | 9000 | 9720
Harness materials (built in-house) | Vendors | WP | 800 | 864
Shipping, customs, logistics | Vendors | WP | 3500 | 3780
Total |  |  | 78200 | 84456
Illustrative amounts for the exercise; check real quotes on the RFQ date. Expensive items may be customer-furnished (CFE).